## Tabular Burn-Down Chart
Release One Burn-Down Chart
Iteration One - Desktop Interface and Advanced Input
Task ID | Task Description | Completing Member(s) | Checking Member(s) | Time Estimate | Time Required | Est. Comp. Date | Comp. Date | Task Points | Rem. Task Points
1 | Design the basic structure for the desktop application. | Mark Powell | Alvin Liu | 3 Hours | 2.5 Hours | 2012-09-26 | 2012-09-27 | 9 | 134
2 | Create the initial opening desktop application tab. | Mark Powell | Alvin Liu | 2 Hours | 3 Hours | 2012-09-27 | 2012-09-27 | 3 | 131
3 | Research the effect of shade on the system and how it should be measured. | Anthony Pitts | Matthew Martin | 3 Hours | 3 Hours | 2012-09-28 | 2012-09-27 | 4 | 127
4 | Create an algorithm to determine the new power output of the system based on the specified shade level. | Anthony Pitts | Matthew Martin | 3 Hours | 3 Hours | 2012-09-29 | 2012-09-30 | 4 | 123
5 | Add in the option to choose your panel type into the desktop application. | Mark Powell | Matthew Martin | 1 Hour | 1 Hour | 2012-09-30 | 2012-09-30 | 3 | 120
6 | Add in the option to choose your panel facing direction into the desktop application. | Mark Powell | Matthew Martin | 1 Hour | 1 Hour | 2012-10-01 | 2012-10-01 | 3 | 117
7 | Add in the option to choose your angle of elevation into the desktop application. | Mark Powell | Alvin Liu | 1 Hour | 1 Hour | 2012-10-02 | 2012-10-01 | 3 | 114
8 | Add in the option to choose your location into the desktop application. | Mark Powell | Matthew Martin | 1 Hour | 1 Hour | 2012-10-03 | 2012-10-04 | 3 | 111
9 | Research the effect of different inverters and how they affect the output of the system. | Joel Harman | Alvin Liu | 2 Hours | 1.5 Hours | 2012-10-04 | 2012-10-04 | 5 | 106
10 | Create an algorithm to determine the new power output of the system based on the inverter specified. | Joel Harman | Mark Powell | 2 Hours | 2.5 Hours | 2012-10-05 | 2012-10-06 | 4 | 102
11 | Add in an input field to the calculator page to allow for the user to enter their desired inverter. | Matthew Martin | Joel Harman | 1 Hour | 1.5 Hours | 2012-10-06 | 2012-10-06 | 3 | 99
12 | Link the input field to the algorithm to fully integrate it into the system. | Joel Harman | Alvin Liu | 1 Hour | 2 Hours | 2012-10-07 | 2012-10-07 | 3 | 96
13 | Add in an input field to enter the estimated daily electricity usage into the desktop application. | Mark Powell | Anthony Pitts | 1 Hour | 1 Hour | 2012-10-08 | 2012-10-07 | 3 | 93
14 | Add in an option to enter the electricity feed-in tariff into the desktop application. | Mark Powell | Anthony Pitts | 1 Hour | 1 Hour | 2012-10-08 | 2012-10-07 | 3 | 90
15 | Add in an option to enter the current panel age into the desktop application. | Mark Powell | Anthony Pitts | 1 Hour | 1 Hour | 2012-10-08 | 2012-10-08 | 3 | 87
16 | Research the various common costs associated with the operation of a solar power system. | Joel Harman | Alvin Liu | 2 Hours | 3 Hours | 2012-10-09 | 2012-10-08 | 5 | 82
17 | Create an algorithm to consider the effect of these consts on the output of the system. | Joel Harman | Alvin Liu | 2 Hours | 2.5 Hours | 2012-10-09 | 2012-10-08 | 3 | 79
18 | Include the algorithm in the main power calculations of the system. | Joel Harman | Alvin Liu | 2.5 Hours | 2.5 Hours | 2012-10-09 | 2012-10-10 | 2 | 77
19 | Link up the various inputs in the desktop application to the appropriate backend calculator. | Anthony Pitts | Matthew Martin | 5 Hours | 7 Hours | 2012-10-10 | 2012-10-10 | 9 | 68
Iteration Two - Focus on Detailed Output and System Usability
Task ID | Task Description | Completing Member(s) | Checking Member(s) | Time Estimate | Time Required | Est. Comp. Date | Comp. Date | Task Points | Rem. Task Points
20 | Research the various expected system each month over a one year period. | Matthew Martin | Alvin Liu | 3 Hours | 3 Hours | 2012-10-10 | 2012-10-11 | 5 | 63
21 | Create an algorithm to break the power from a given year up into its respective months. | Matthew Martin | Alvin Liu | 2 Hours | 3 Hours | 2012-10-10 | 2012-10-11 | 4 | 59
22 | Create a link on each year of the table which links to a month-by-month breakdown for the specified year. | Anthony Pitts | Joel Harman | 2 Hours | 3 Hours | 2012-10-11 | 2012-10-11 | 3 | 56
23 | Determine the information which is most critical to be displayed on a printable information sheet. | Anthony Pitts | Joel Harman | 2 Hours | 2 Hours | 2012-10-12 | 2012-10-14 | 3 | 53
24 | Determine how the inforamtion should be arranged for best appearance on the page. | Matthew Martin | Anthony Pitts | 2 Hours | 2 Hours | 2012-10-13 | 2012-10-14 | 3 | 50
25 | Add a button to link to the printable information sheets. | Joel Harman | Mark Powell | 2 Hours | 2 Hours | 2012-10-14 | 2012-10-14 | 3 | 47
26 | Create a separate page for displaying the information in a printable format. | Joel Harman | Mark Powell | 3 Hours | 4 Hours | 2012-10-15 | 2012-10-17 | 4 | 43
27 | Research the various common Australian electricity tarrifs. | Anthony Pitts | Matthew Martin | 2 Hours | 3 Hours | 2012-10-16 | 2012-10-17 | 6 | 37
28 | Replace the tariff input box with a drop down box showing all of the common Australian tariffs. | Anthony Pitts | Joel Harman | 2 Hours | 1.5 Hours | 2012-10-17 | 2012-10-17 | 3 | 34
29 | Modify the graphing code to allow for both x and y title information, to more accurately convey the information from the graph. | Joel Harman | Mark Powell | 3 Hours | 4 Hours | 2012-10-18 | 2012-10-18 | 4 | 30
30 | Modify the graphing calls to work with the updated inputs, giving each their appropriate title information. | Joel Harman | Mark Powell | 1 Hour | 2 Hours | 2012-10-19 | 2012-10-18 | 4 | 26
31 | Research the common uses, benefits and reasons for why users may wish to use solar power systems. | Matthew Martin | Anthony Pitts | 2 Hours | 2 Hours | 2012-10-20 | 2012-10-20 | 4 | 22
32 | Provide much more helpful information on the startup pages, to better give users an understanding of solar power systems and their benefits. | Matthew Martin | Anthony Pitts | 2 Hours | 2 Hours | 2012-10-21 | 2012-10-20 | 3 | 19
33 | Develop a new system design for the web application interface. | Mark Powell | Alvin Liu | 8 Hours | 8 Hours | 2012-10-22 | 2012-10-23 | 8 | 11
34 | Implement the new website layout for the web application interface. | Joel Harman | Alvin Liu | 4 Hours | 4 Hours | 2012-10-23 | 2012-10-23 | 8 | 3
35 | Provide more effective form validation to ensure users always understand where their errors have occurred. | Joel Harman | Alvin Liu | 1 Hour | 2 Hours | 2012-10-24 | 2012-10-24 | 3 | 0

## Task Point Breakdown
Story Point Burn-Down
Day | Est. Points Remaining | Points Remaining
1 | 143 | 143
2 | 137.2 | 127
3 | 131.4 | 127
4 | 125.6 | 127
5 | 119.8 | 120
6 | 114 | 114
7 | 108.2 | 114
8 | 102.4 | 114
9 | 96.6 | 106
10 | 90.8 | 106
11 | 85 | 99
12 | 79.2 | 89
13 | 73.4 | 79
14 | 68 | 68
15 | 63 | 68
16 | 58 | 56
17 | 53 | 56
18 | 48 | 56
19 | 43 | 49
20 | 38 | 49
21 | 33 | 49
22 | 28 | 34
23 | 23 | 26
24 | 18 | 26
25 | 13 | 19
26 | 8 | 19
27 | 3 | 7
28 | 0 | 0

## Test Breakdown
Release One Test Breakdown
Unit Tests
Test # | Test Description | Passes
1 | Empty constructor test. Checks to ensure an empty constructor can be initialised. | ü
2 | Main constructor test. Checks to ensure that a constructor can be initialised with all main calculator inputs. | ü
3 | Sum Result test. Checks to ensure that an empty list can be summed correctly. | ü
4 | Sum Result test. Checks to ensure that a positive list can be summed correctly. | ü
5 | Sum Result test. Checks to ensure that a mixed list, including decimals, can be summed correctly. | ü
6 | Sum Result test. Checks to ensure that an exception will trigger if a null list is parsed for calculation. | ü
7 | Average Result test. Checks to ensure that if an average from an empty list is requested, an exception is returned. | ü
8 | Average Result test. Checks to ensure that averages calculate correctly in positive lists. | ü
9 | Average Result test. Checks to ensure that averages calculate correctly in mixed, decimal lists. | ü
10 | Average Result test. Checks to ensure that an exception will trigger if a null list is parsed for calculation. | ü
11 | Electricity Generation test with positive power. Checks to ensure that yearly electricity generation values are calculated correctly. | ü
12 | Electricity Generation test with zero power. Checks to ensure that yearly electricity generation values are calculated correctly. | ü
13 | Electricty Generation test with negative power. Checks to ensure that an exception is triggered. | ü
14 | Lifetime Savings with positive list. Checks to ensure result is calculated correctly. | ü
15 | Lifetime Savings with empty list. Check to ensure that a zero list is returned. | ü
16 | Lifetime Savings with null list. Check to ensure that an exception is triggered. | ü
17 | Lifetime Savings with different sized list than expected. Check to ensure exception is triggered. | ü
18 | Carbon Savings with positive list. Checks to ensure result is calculated correctly. | ü
19 | Carbon Savings with empty list. Checks to ensure that a zero list is returned. | ü
20 | Carbon Savings with null list. Checks to ensure that an exception is triggered. | ü
21 | Carbon Savings with different sized list than expected. Checks to ensure exception is triggered. | ü
22 | Back Investment test. Checks to ensure that the final result is calculated correctly. | ü
23 | Bank Investment test with a less than one input. Checks to ensure that the final result is calculated correctly. | ü
24 | Bank investment test with a negative input. Checks to ensure that an exception is triggered correctly. | ü
25 | Bank Investment test with a zero input. Checks to ensure that an exception is fired correctly. | ü
26 | Panel investment test with mixed array. Checks to ensure that the return is calculated correctly. | ü
27 | Panel investment test with a zero length array. Checks to ensure that an exception is thrown accordingly. | ü
28 | Panel investment test with a null array. Checks to ensure that an exception is thrown correctly. | ü
29 | Panel invetsment test with different sized list than expected. Checks to ensure that an exception is thrown correctly. | ü
30 | Break-Even test with expected break even. Checks to ensure that the break-even time is calculated correctly. | ü
31 | Break-Even test with no expected break even. Checks to ensure that the appropriate message value is returned. | ü
32 | Break-Even test with borderline break even. Checks to ensure that the break even is calculated correctly. | ü
33 | Break-Even test with empty savings array. Checks to ensure that the appropriate break even time is returned. | ü
34 | Break-Even test with null savings array. Checks to ensure that an exception is thrown correctly. | ü
35 | Calculate excess power generation test with regular inputs. Checks to ensure that the correct outputs are returned. | ü
36 | Calculate excess power generation test with an empty power input. Checks to ensure that the correct outputs are returned. | ü
37 | Calculate excess power generation test with a null input. Checks to ensure that an exception is triggered correctly. | ü
38 | Calculate excess power generation test with negative inputs. Checks to ensure that the correct inputs are returned. | ü
39 | Calculate excess power earnings with regular inputs. Checks to ensure that the correct outputs are returned. | ü
40 | Calculate excess power earnings with empty power input. Checks to ensure that the correct results are returned. | ü
41 | Calculate excess power earnings with negative power inputs. Checks to ensure the correct results are returned. | ü
42 | Calculate excess power earnings with power over that which is generated. Checks to ensure correct results are returned. | ü
43 | Calculate excess power earnings with power under that which is used. Checks to ensure correct results are returned. | ü
44 | Calculate excess power earnings with a null power input. Checks to ensure an exception is thrown correctly. | ü
45 | Calculate panel generation percent test with regular inputs. Checks to ensure results are calculated correctly. | ü
46 | Calculate panel generation percent test with zero length. Checks to ensure correct results are returned. | ü
47 | Calculate panel generation percent test with null input. Checks to ensure that an exception is triggered correctly. | ü
48 | Panel Wattage Accessor Test. | ü
49 | Panel Wattage Mutator Test. | ü
50 | Angle of Installation Accessor Test. | ü
51 | Angle of Installation Mutator Test. | ü
52 | Panel Ground Angle Accessor Test. | ü
53 | Panel Ground Angle Mutator Test. | ü
54 | Hours of Daylight Accessor Test. | ü
55 | Hours of Daylight Mutator Test. | ü
56 | Savings Per Kilowatt Accessor Test. | ü
57 | Savings Per Kilowatt Mutator test. | ü
58 | System Cost Accessor Test. | ü
59 | System Cost Mutator test. | ü
60 | Feed-In Tariff Accessor Test. | ü
61 | Feed-In Tariff Mutator Test. | ü
62 | Cost Per Watt Accessor Test. | ü
63 | Cost Per Watt Mutator Test. | ü
64 | Electricity Generation Acessor Test. | ü
65 | Electricity Generator Mutator Test. | ü
Integration Tests
Test # | Test Description | Passes
1 | Panel Choice Selection. Simple check to ensure that it is usable in the web application as it is the first element. Radio boxes work appropriately and link to correct images. | ü
2 | Panel Facing Selection. Check to ensure it fits in with the choice selection and the drop-down menu allows all options to be selected appropriately. | ü
3 | Panel angle input. Check to ensure users are able to enter their desired angle in correctly and it fits appropriately with the other input options. | ü
4 | Result output. Check to ensure that the form correctly links to the results page, feeding the correct values to the calculator. | ü
5 | Panel Choice Selection #2. Check to ensure that changing the choice of panel correctly affects the results specified. | ü
6 | Panel Facing Selection #2. Check to ensure that changing the facing of the panel correctly affects the results specified. | ü
7 | Panel Angle input #2. Check to ensure that changing the angle of the panels correctly affects the results specified. | ü
8 | Overall totals. Check to ensure that the overall totals are specified correctly when appended to the results table. | ü
9 | Feed-In Tariff input test. Check to ensure that it fits in with the inputs page correctly, and changing the value correctly affects the outputs specified. | ü
10 | Greenhouse Gas reduction test. Check to ensure that the additional column provides correct data corresponding to the output power generation. | ü
11 | Totals summary test. Check to ensure that the total summaries for all important data match up with the expected data. | ü
12 | Investment integration test #1. Check to ensure that the investment returns match up with the estimated savings calculated previously. | ü
13 | Investment integration test #2. Check that the investment break even time specified matches up with what the data suggests. | ü
14 | Investment integration test #3. Check that the value specified in net profit matches up with what should be expected from the total, minus the system cost. | ü
15 | Investment integration test #4. Check to ensure that the bank investment starts at the same initial value as the panel investment. | ü
16 | Investment integration test #5. Check to ensure that the total end bank investment value specified matches up with what the data is showing. | ü
17 | Earnings integration test #1. Check to ensure that modifying the excess feed-in value also affects the expected return appropriately. | ü
18 | Earnings integration test #2. Check to ensure that the estimated savings directly correspond with the expected power generation values. | ü
19 | Graph integration test. Check to ensure that the values shown on each of the graphs match up with their table equivalents. | ü
20 | Existing user summary. Check the existing user summary to ensure that at the time specified, the values match with what is expected (by viewing tabulated information further down the page). | ü
System Tests
Test # | Test Description | Passes
1 | Check to ensure that an outside user is able to navigate the web application to the calculator. | ü
2 | Check to ensure that an outside user is able to understand all of the terminology in the calculator (assuming they look at the terminology/information page). | ü
3 | Check to ensure that an outside user is able to understand how to input all inormation and retrieve their results. | ü
4 | Check to ensure that an ourside user is able to view the results page and understand what each section means. | ü
5 | Check to ensure that an outside user is able to understand and interpret the graphical outputs and undestand what each section means. | ü
6 | Check to ensure that the site loads and retrieves information in a reasonable amount of time (< 2 seconds). | ü
7 | Check to ensure that incorrect information will inform users of their mistakes and how they can be fixed. | ü
8 | Check to ensure that the application runs sucessfully on the main browsers (IE, Firefox, Chrome, Opera etc). | ü
Non-Functional Acceptance Tests
Test # | Test Description | Passes
1 | Electricity Generation (St. 1): Output is measured on a yearly basis for the lifetime of the product. | ü
2 | Electricity Generation (St. 1): Output is measured in megawatts. | ü
3 | Electricity Generation (St. 1): Each year should be displayed seperately. | ü
4 | Potential Purchaser (St. 2): Multiple common panel options are available for the user to choose between. | ü
5 | Potential Purchaser (St. 2): Each panel has its own power generation, degredation and lifespan with which results are calculated. | ü
6 | Panel Cost Savings (St. 3): Cost savings are in dollar format, with values specified as yearly amounts. | ü
7 | Panel Carbon Savings (St. 4): Carbon savings are displayed in metric tonnes, on a yearly basis. | ü
8 | Break-Even (St. 5): Break even cost is displayed as number of years since the product purchase. | ü
9 | Total Lifetime Savings (St.6): An estimated range of savings is provided, to account for potential variation. | ü
10 | Lifetime Panel Degredation (St. 7): Actual power generation is displayed in medgawatts. With consecutive years displayed side by side. | ü
11 | Total Panel Generation (St. 8): Power genration must exceed specifications for a minimum of ten years. | ü
12 | Potential Earnings (St. 9): Excess power is estimated based on estimated usage and expected generation. | ü
13 | Climate Impact (St. 12): Users are able to select the area they wish to calculate results for. | ü
14 | Comparisons with Other Investments (St. 19): Comparison results are clearly displayed side-by-side for easy comparison. | ü
15 | Error Descriptors (St. 42): All errors should display at least one message. | ü
16 | Error Descriptors (St. 42): All errors should indicate how they can be avoided, not just why they occurred. | ü
17 | Panel Terminology (St. 11): All terminology used on both the calculator and results page is present in the terminology page. | ü
18 | Disclaimer (St. 39): The disclaimer will be shown to all users of the calculator. | ü
19 | Decline in energy generation (St. 21): The decline should easily be viewable, with the data for consecutive years clearly shown side by side. | ü
Functional Acceptance Tests
Test # | Test Description | Passes
1 | If the panel wattage doubles, the electricity generated should also double. Any panel increases should directly correspond to power increases. | ü
2 | A panel angle of 45 degrees should cut estimated power generation by 25%. | ü
3 | A panel angle of 90 degrees should cut estimated power by 50%. | ü
4 | A panel angle of 22 degrees should cut estimated power by 12.2%. | ü
5 | A panel facing of south should cut estimated power by 30% (when compared to north placement). | ü
6 | A panel facing of north-east should cut estimated power by 7.5% (when compared to a north placement). | ü
7 | A panel facing of south-west should cut estimated power by 22.5% (when compared to a north placement). | ü
8 | Doubling the cost of electricity should also double the estimated savings from the solar panels. | ü
9 | Doubling the feed-in tariff should double the estimated money generated due to excess power. | ü
10 | Increasing the daily usage by 1kW should show a decline in excess power by 365.25kW per year. | ü
11 | Choosing Sydney instead of Brisbane should show an energy improvement by approximately 19%. | ü
12 | A north facing panel of 4000W placed at a 10 degree angle of elevation in Brisbane should generate a total of 90568kW of power over its lifetime. | ü
13 | A south facing panel of 3000W placed at a 15 degree angle of elevation in Brisbane should have an average yearly power generation of 3074kW, $400 yearly savings and prevent 6258 tonnes of tarbon emission. | ü
14 | An east facing panel of 1000W placed at an 80 degree angle of elevation in Sydney should have a total carbon savings of 30719 tonnes. | ü

## Stories Completed
Release One Story Breakdown
Story ID | Story Description | Story Points | Cummulative Total
16 | House Specification: As a potential purchaser I would like to be able to put in the specifications of my room so that I can receive results specific to my installation. | 9 | 9
1 | Electricity Generation: As a Potential Purchaser I want to see how much electricity I am likely to generate so that I can compare it to my actual usage. | 8 | 17
2 | Varied Panel Electricity Generation: As a potential purchaser I want to see the potential generation from a variety of panel configurations. | 8 | 25
3 | Varied Panel Cost Savings: As a Potential Purchaser I want to see the potential yearly cost savings from a variety of panel sizes. | 8 | 33
4 | Varied Panel Carbon Savings: As a Potential Purchaser I want to see the potential yearly carbon savings from a variety of panel sizes. | 7 | 40
8 | Total power generation: As a potential purchaser I want to see the total power the system is likely to generate for me over its lifetime so that I can determine its actual value. | 7 | 47
6 | Total lifetime savings: As a potential purchaser I want to see how much money the unit will save me over its lifetime so that I can determine its actual value. | 7 | 54
5 | Price Break-Even: As a potential purchaser I want to see how long it will take the unit to break even in costs so that I can determine whether the investment is worth it. | 7 | 61
12 | Climate Impact: Asd a potential purchaser, I want to see how the climate of an area impacts on the results shown so that I can determine how effective the panels are in my area. | 6 | 67
8 | Total Panel Generation: As a potential purchaser, I want to see the total number of solar panels required to meet my expected demand so that I am not reliant on the power grid. | 6 | 73
9 | Potential Energy Earnings: As a potential purchaser I want to se the potential earnings I can receive from excess energy generation so that I can see if the investment is worthwhile. |  | 73
19 | Compare Investments: As a potential purchaser I want to be able to compare the return on investment from the solar panel with other low-risk investments, so that I can see the true contextual benefit of the installation. | 4 | 77
21 | As an existing owner I want to see the decline in energy generation over the lifetime of the product so that I can determine when to replace the unit. | 6 | 83
28 | As an existing owner I want to be able to see the total estimated money the system has saved for me since it was installed so that I can determine its current benefit. | 6 | 89
29 | As a sales person I want a simple summary of the expected return on investment so that I can provide a convincing argument for potential customers. | 7 | 96
36 | Comparison of Panel Returns with Investments: As a sales person I want to be able to compare the return from the solar panels with other potential investments, so that I can show clients the effectiveness of the system. | 5 | 101
39 | Disclaimer Information: As an installation company I want a clear disclaimer shown to clients so that they understand the nature of the estimate, its reliance on their data and that the calculator is meant as a guide rather than an accurate tool. | 5 | 106
42 | Error Descriptors: As a potential purchaser I want to receive detailed error messages if input mistakes are made so I can easily determine and fix problems. | 5 | 111
11 | Panel Terminology: As a potential purchaser I want to see detailed information and definitions regarding solar panel terminology so that I can satisfactorily understand the functionality of the application and its purpose in order to achieve a relevant result. | 5 | 116