## Tabular Burn-Down Chart
Release One Burn-Down Chart
Iteration One - Basic Functionality, with focus on new users.
Task ID | Task Description | Completing Member(s) | Checking Member(s) | Time Estimate | Time Required | Est. Comp. Date | Comp. Date | Task Points | Rem. Task Points
1 | Download/Install Eclipse, Java SDK, Eclipse App Engine plug-in and Github. | ALL | N/A | 15 Hours | 25 Hours | 2012-08-23 | 2012-08-26 | 8 | 185
2 | Complete online Google App Engine tutorials to learn the basics of the environment. | ALL | N/A | 30 Hours | 25 Hours | 2012-08-24 | 2012-09-27 | 10 | 175
3 | Upload the example files to the remote Git repository. | ALL | N/A | 3 Hours | 4 Hours | 2012-08-24 | 2012-08-27 | 4 | 171
4 | Check that files committed by other users are able to be accessed and modified appropriately. | ALL | ALL | 3 Hours | 6 Hours | 2012-08-24 | 2012-08-28 | 4 | 167
5 | Research potential panel options to determine common configurations. | Anthony Pitts | Matthew Martin | 4 Hours | 2 Hours | 2012-08-25 | 2012-08-28 | 2 | 165
6 | Add a variety of panels to the Google Apps Database. | Anthony Pitts | Matthew Martin | 3 Hours | 2 Hours | 2012-08-25 | 2012-08-28 | 3 | 162
7 | Add a selection menu, with basic descriptions and radio boxes for each of the panel types. | Joel Harman | Mark Powell | 3 Hours | 4 Hours | 2012-08-25 | 2012-08-28 | 2 | 160
8 | Research effects of panel facing on the output of a solar panel. | Anthony Pitts | Matthew Martin | 2 Hours | 3 Hours | 2012-08-26 | 2012-08-29 | 2 | 158
9 | Add panel facing direction options to the calculator menu. | Joel Harman | Alvin Liu | 2 Hours | 2 Hours | 2012-08-26 | 2012-08-29 | 1 | 157
10 | Implement the algorithm to consider the panel facing in all calculations. | Matthew Martin | Mark Powell | 2 Hours | 2 Hours | 2012-08-26 | 2012-08-29 | 2 | 155
11 | Research the effects of panel angle changes on the output of a solar panel. | Matthew Martin | Mark Powell | 2 Hours | 3 Hours | 2012-08-27 | 2012-08-29 | 2 | 153
12 | Add panel angle options to the calculator menu. | Joel Harman | Alvin Liu | 2 Hours | 1 Hour | 2012-08-27 | 2012-08-29 | 1 | 152
13 | Implement the algorithm to consider the panel angle changes in the calcuator outputs. | Alvin Liu | Anthony Pitts | 2 Hours | 2 Hours | 2012-08-27 | 2012-08-29 | 2 | 150
14 | Research the effects on how each of these factors effect the total generation of a solar panel output. | Alvin Liu | Anthony Pitts | 2 Hours | 3 Hours | 2012-08-28 | 2012-08-29 | 2 | 148
15 | Develop an algorithm for determining the power output based on Brisbane data at the time of installation. | Mark Powell | Joel Harman | 3 Hours | 4 Hours | 2012-08-28 | 2012-08-30 | 4 | 144
16 | Modify the algorithm to allow for calculating yearly values, considering panel degredation. | Mark Powell | Joel Harman | 1.5 Hours | 1.5 Hours | 2012-08-28 | 2012-08-30 | 3 | 141
17 | Create a new page for displaying outputs from panel calculations. | Joel Harman | Alvin Liu | 2 Hours | 3 Hours | 2012-08-29 | 2012-08-30 | 2 | 139
18 | Add the yearly panel power outputs to a table in the results page. | Joel Harman | Alvin Liu | 2.5 Hours | 2.5 Hours | 2012-08-29 | 2012-08-30 | 1 | 138
19 | Add an input field to allow the user to enter their power feed-in tariffs. | Joel Harman | Alvin Liu | 1 Hour | 2 Hour | 2012-08-29 | 2012-08-30 | 1 | 137
20 | Create an algorithm for determining yearly money savings based on power generation and power cost. | Alvin Liu | Mark Powell | 2 Hours | 3 Hours | 2012-08-30 | 2012-08-31 | 3 | 134
21 | Add an additional column to the results table to reflect the cost savings. | Joel Harman | Alvin Liu | 2 Hours | 1 Hour | 2012-08-30 | 2012-08-31 | 2 | 132
22 | Research the expected greenhouse gas reductions from solar panels. | Matthew Martin | Mark Powell | 1.5 Hours | 2 Hours | 2012-08-30 | 2012-09-01 | 2 | 130
23 | Create an algorithm to determine carbon savings from panel electricity generation. | Matthew Martin | Mark Powell | 2 Hours | 2 Hours | 2012-08-31 | 2012-09-01 | 2 | 128
24 | Add a column to the results table showing expected yearly carbon savings. | Joel Harman | Alvin Liu | 2 Hours | 1 Hour | 2012-08-31 | 2012-09-01 | 1 | 127
25 | Create an algorithm to determine total results based on yearly breakdowns. | Anthony Pitts | Joel Harman | 2 Hours | 2 Hours | 2012-08-31 | 2012-09-01 | 2 | 125
26 | Create a separate results section to show totals for all values (power, savings, carbon reductions etc). | Joel Harman | Anthony Pitts | 2 Hours | 2 Hours | 2012-09-01 | 2012-09-01 | 2 | 123
27 | Add total values to the bottom of the breakdown table. | Joel Harman | Anthony Pitts | 1 Hour | 1 Hour | 2012-09-01 | 2012-09-01 | 2 | 121
28 | Create an algorithm to determine average yearly results based on yearly breakdowns. | Anthony Pitts | Mark Powell | 2 Hours | 2 Hours | 2012-09-02 | 2012-09-02 | 3 | 118
29 | Add in the average values for all major outputs in the new results section. | Joel Harman | Alvin Liu | 3 Hours | 3 Hours | 2012-09-02 | 2012-09-02 | 2 | 116
30 | Create an algorithm to determine average daily results based on average yearly results. | Anthony Pitts | Alvin Liu | 1 Hour | 1 Hour | 2012-09-02 | 2012-09-02 | 1 | 115
31 | Display the average daily results alongside yearly amounts for easier readability. | Joel Harman | Matthew Martin | 1 Hour | 1 Hour | 2012-09-02 | 2012-09-03 | 1 | 114
32 | Create an algorithm for determining yearly investment values for a solar panel over its lifetime. | Joel Harman | Matthew Martin | 3 Hours | 3 Hours | 2012-09-03 | 2012-09-03 | 4 | 110
33 | Create an algorithm for determining yearly investment values for a standard investment. | Mark Powell | Matthew Martin | 2 Hours | 2 Hours | 2012-09-03 | 2012-09-04 | 4 | 106
34 | Create a separate section in the results page for displaying the solar panel investment alongside the bank investment. | Joel Harman | Alvin Liu | 2 Hours | 2 Hours | 2012-09-03 | 2012-09-04 | 4 | 102
35 | Create an algorithm for determining the break-even time for the product, using the panel investment algorithm. | Mark Powell | Alvin Liu | 2 Hours | 2 Hours | 2012-09-04 | 2012-09-04 | 4 | 98
36 | Add a label to display the estimated break-even time for the product given the specified inputs. | Joel Harman | Mark Powell | 1 Hour | 1 Hour | 2012-09-04 | 2012-09-04 | 2 | 96
37 | Research the effects of excess power generation (other that which is being consumed) for a solar panel. | Anthony Pitts | Joel Harman | 4 Hours | 5 Hours | 2012-09-04 | 2012-09-04 | 3 | 93
38 | Add an input field in the calculator page to allow users to enter their excess power generation tariff. | Joel Harman | Anthony Pitts | 1 Hour | 1 Hour | 2012-09-05 | 2012-09-04 | 2 | 91
39 | Create an algorithm to determine the amount of money generated from power over that which is being consumed. | Anthony Pitts | Matthew Martin | 2 Hours | 3 Hours | 2012-09-05 | 2012-09-06 | 3 | 88
40 | Add a separate section to the results page for information related to excess earnings. | Joel Harman | Matthew Martin | 1 Hour | 2 Hour | 2012-09-05 | 2012-09-06 | 2 | 86
41 | Add in year-by-year breakdowns of how much money will be generated from excess earnings. | Alvin Liu | Mark Powell | 3 Hours | 3 Hours | 2012-09-06 | 2012-09-06 | 3 | 83
42 | Develop an algorithm for determining the panels required to completely generate solar power from panels, for a minimum of ten years. | Alvin Liu | Mark Powell | 2 Hours | 3 Hours | 2012-09-06 | 2012-09-06 | 3 | 80
43 | Add a label to the earnings section which displays the wattage needed to achieve total panel power generation. | Joel Harman | Alvin Liu | 1 Hour | 1 Hour | 2012-09-06 | 2012-09-06 | 2 | 78
Iteration Two - Focus on Usability and User Information.
Task ID | Task Description | Completing Member(s) | Checking Member(s) | Time Estimate | Time Required | Est. Comp. Date | Comp. Date | Task Points | Rem. Task Points
44 | Update the calculator with improved graphics for easier usability. | Joel Harman | ALL | 10 Hours | 15 Hours | 2012-09-08 | 2012-09-06 | 8 | 78
45 | Update the calculator to include graphs in all areas which describe yearly breakdown figures. | Joel Harman | ALL | 5 Hours | 4 Hours | 2012-09-09 | 2012-09-06 | 7 | 71
46 | Add in reasonable default values to each of the specified inputs. | Mark Powell | Joel Harman | 3 Hours | 3.5 Hours | 2012-09-09 | 2012-09-07 | 6 | 65
47 | Add a page to the web interface to provide users with important solar panel terminology. | Matthew Martin | Anthony Pitts | 4 Hours | 4.5 Hours | 2012-09-10 | 2012-09-09 | 5 | 60
48 | Add in form validation to ensure all values specified are appropriate inputs before submission. | Matthew Martin | Anthony Pitts | 3 Hours | 4 Hours | 2012-09-10 | 2012-09-09 | 5 | 55
49 | Add a home page to provide users with a description of the purpose and usage of the calculator. | Joel Harman | Mark Powell | 2 Hours | 2 Hours | 2012-09-11 | 2012-09-09 | 5 | 50
50 | Add a disclaimer message to both the input and results pages to inform users that all values are esimates only. | Matthew Martin | Mark Powell | 1 Hour | 1.5 Hours | 2012-09-11 | 2012-09-10 | 4 | 46
51 | Research the effects of weather on different parts of Australia. | Anthony Pitts | Matthew Martin | 3 Hours | 4 Hours | 2012-09-12 | 2012-09-12 | 5 | 41
52 | Add to the Google Datastore available locations and their estimated daylight hours. | Anthony Pitts | Joel Harman | 2.5 Hours | 3 Hours | 2012-09-12 | 2012-09-12 | 3 | 38
53 | Add in an additional input field to allow the user to specify their location. | Joel Harman | Mark Powell | 2 Hours | 1.5 Hours | 2012-09-13 | 2012-09-13 | 3 | 35
54 | Add in an option for existing users to enter the current life of their panel (in years). | Joel Harman | Mark Powell | 2 Hours | 1 Hour | 2012-09-13 | 2012-09-13 | 5 | 30
55 | Develop an algorithm to determine the expected amount of power generated to date (if existing user). | Mark Powell | Anthony Pitts | 2 Hours | 2.5 Hours | 2012-09-14 | 2012-09-15 | 3 | 27
56 | Develop an algorithm to determine the expected amount of money saved to date (if existing user). | Mark Powell | Alvin Liu | 2 Hours | 2.5 Hours | 2012-09-14 | 2012-09-15 | 3 | 24
57 | Develop an algorithm to determine the expected amount of carbon emission reductions to date (if existing user). | Mark Powell | Alvin Liu | 2 Hours | 1 Hour | 2012-09-15 | 2012-09-15 | 3 | 21
58 | Develop an algorithm to determine the current expected power generation (if an existing user). | Mark Powell | Alvin Liu | 2 Hours | 1 Hour | 2012-09-15 | 2012-09-16 | 3 | 18
59 | Create a new "existing user" section to the results page, but only shown if a current panel age is specified. | Joel Harman | Alvin Liu | 4 Hours | 5 Hours | 2012-09-16 | 2012-09-17 | 5 | 13
60 | Create output labels/graphs showing the current and cummulitive totals to date for all important pieces of information. | Joel Harman | Alvin Liu | 4 Hours | 5 Hours | 2012-09-16 | 2012-09-18 | 5 | 8

## Task Point Breakdown
Story Point Burn-Down
Day | Est. Points Remaining | Points Remaining
1 | 193 | 193
2 | 185 | 193
3 | 167 | 193
4 | 160 | 185
5 | 155 | 171
6 | 150 | 160
7 | 141 | 148
8 | 137 | 137
9 | 130 | 132
10 | 125 | 121
11 | 121 | 115
12 | 114 | 110
13 | 105 | 91
14 | 96 | 91
15 | 89 | 63
16 | 81 | 57
17 | 73 | 57
18 | 65 | 42
19 | 58 | 38
20 | 52 | 38
21 | 46 | 30
22 | 38 | 22
23 | 32 | 22
24 | 26 | 13
25 | 20 | 10
26 | 14 | 5
27 | 6 | 0
28 | 0.42858 | 0

## Test Breakdown
Release One Test Breakdown
Unit Tests
Test # | Test Description | Passes
1 | Empty constructor test. Checks to ensure an empty constructor can be initialised. | ü
2 | Main constructor test. Checks to ensure that a constructor can be initialised with all main calculator inputs. | ü
3 | Sum Result test. Checks to ensure that an empty list can be summed correctly. | ü
4 | Sum Result test. Checks to ensure that a positive list can be summed correctly. | ü
5 | Sum Result test. Checks to ensure that a mixed list, including decimals, can be summed correctly. | ü
6 | Sum Result test. Checks to ensure that an exception will trigger if a null list is parsed for calculation. | ü
7 | Average Result test. Checks to ensure that if an average from an empty list is requested, an exception is returned. | ü
8 | Average Result test. Checks to ensure that averages calculate correctly in positive lists. | ü
9 | Average Result test. Checks to ensure that averages calculate correctly in mixed, decimal lists. | ü
10 | Average Result test. Checks to ensure that an exception will trigger if a null list is parsed for calculation. | ü
11 | Electricity Generation test with positive power. Checks to ensure that yearly electricity generation values are calculated correctly. | ü
12 | Electricity Generation test with zero power. Checks to ensure that yearly electricity generation values are calculated correctly. | ü
13 | Electricty Generation test with negative power. Checks to ensure that an exception is triggered. | ü
14 | Lifetime Savings with positive list. Checks to ensure result is calculated correctly. | ü
15 | Lifetime Savings with empty list. Check to ensure that a zero list is returned. | ü
16 | Lifetime Savings with null list. Check to ensure that an exception is triggered. | ü
17 | Lifetime Savings with different sized list than expected. Check to ensure exception is triggered. | ü
18 | Carbon Savings with positive list. Checks to ensure result is calculated correctly. | ü
19 | Carbon Savings with empty list. Checks to ensure that a zero list is returned. | ü
20 | Carbon Savings with null list. Checks to ensure that an exception is triggered. | ü
21 | Carbon Savings with different sized list than expected. Checks to ensure exception is triggered. | ü
22 | Back Investment test. Checks to ensure that the final result is calculated correctly. | ü
23 | Bank Investment test with a less than one input. Checks to ensure that the final result is calculated correctly. | ü
24 | Bank investment test with a negative input. Checks to ensure that an exception is triggered correctly. | ü
25 | Bank Investment test with a zero input. Checks to ensure that an exception is fired correctly. | ü
26 | Panel investment test with mixed array. Checks to ensure that the return is calculated correctly. | ü
27 | Panel investment test with a zero length array. Checks to ensure that an exception is thrown accordingly. | ü
28 | Panel investment test with a null array. Checks to ensure that an exception is thrown correctly. | ü
29 | Panel invetsment test with different sized list than expected. Checks to ensure that an exception is thrown correctly. | ü
30 | Break-Even test with expected break even. Checks to ensure that the break-even time is calculated correctly. | ü
31 | Break-Even test with no expected break even. Checks to ensure that the appropriate message value is returned. | ü
32 | Break-Even test with borderline break even. Checks to ensure that the break even is calculated correctly. | ü
33 | Break-Even test with empty savings array. Checks to ensure that the appropriate break even time is returned. | ü
34 | Break-Even test with null savings array. Checks to ensure that an exception is thrown correctly. | ü
35 | Calculate excess power generation test with regular inputs. Checks to ensure that the correct outputs are returned. | ü
36 | Calculate excess power generation test with an empty power input. Checks to ensure that the correct outputs are returned. | ü
37 | Calculate excess power generation test with a null input. Checks to ensure that an exception is triggered correctly. | ü
38 | Calculate excess power generation test with negative inputs. Checks to ensure that the correct inputs are returned. | ü
39 | Calculate excess power earnings with regular inputs. Checks to ensure that the correct outputs are returned. | ü
40 | Calculate excess power earnings with empty power input. Checks to ensure that the correct results are returned. | ü
41 | Calculate excess power earnings with negative power inputs. Checks to ensure the correct results are returned. | ü
42 | Calculate excess power earnings with power over that which is generated. Checks to ensure correct results are returned. | ü
43 | Calculate excess power earnings with power under that which is used. Checks to ensure correct results are returned. | ü
44 | Calculate excess power earnings with a null power input. Checks to ensure an exception is thrown correctly. | ü
45 | Calculate panel generation percent test with regular inputs. Checks to ensure results are calculated correctly. | ü
46 | Calculate panel generation percent test with zero length. Checks to ensure correct results are returned. | ü
47 | Calculate panel generation percent test with null input. Checks to ensure that an exception is triggered correctly. | ü
48 | Panel Wattage Accessor Test. | ü
49 | Panel Wattage Mutator Test. | ü
50 | Angle of Installation Accessor Test. | ü
51 | Angle of Installation Mutator Test. | ü
52 | Panel Ground Angle Accessor Test. | ü
53 | Panel Ground Angle Mutator Test. | ü
54 | Hours of Daylight Accessor Test. | ü
55 | Hours of Daylight Mutator Test. | ü
56 | Savings Per Kilowatt Accessor Test. | ü
57 | Savings Per Kilowatt Mutator test. | ü
58 | System Cost Accessor Test. | ü
59 | System Cost Mutator test. | ü
60 | Feed-In Tariff Accessor Test. | ü
61 | Feed-In Tariff Mutator Test. | ü
62 | Cost Per Watt Accessor Test. | ü
63 | Cost Per Watt Mutator Test. | ü
64 | Electricity Generation Acessor Test. | ü
65 | Electricity Generator Mutator Test. | ü
Integration Tests
Test # | Test Description | Passes
1 | Panel Choice Selection. Simple check to ensure that it is usable in the web application as it is the first element. Radio boxes work appropriately and link to correct images. | ü
2 | Panel Facing Selection. Check to ensure it fits in with the choice selection and the drop-down menu allows all options to be selected appropriately. | ü
3 | Panel angle input. Check to ensure users are able to enter their desired angle in correctly and it fits appropriately with the other input options. | ü
4 | Result output. Check to ensure that the form correctly links to the results page, feeding the correct values to the calculator. | ü
5 | Panel Choice Selection #2. Check to ensure that changing the choice of panel correctly affects the results specified. | ü
6 | Panel Facing Selection #2. Check to ensure that changing the facing of the panel correctly affects the results specified. | ü
7 | Panel Angle input #2. Check to ensure that changing the angle of the panels correctly affects the results specified. | ü
8 | Overall totals. Check to ensure that the overall totals are specified correctly when appended to the results table. | ü
9 | Feed-In Tariff input test. Check to ensure that it fits in with the inputs page correctly, and changing the value correctly affects the outputs specified. | ü
10 | Greenhouse Gas reduction test. Check to ensure that the additional column provides correct data corresponding to the output power generation. | ü
11 | Totals summary test. Check to ensure that the total summaries for all important data match up with the expected data. | ü
12 | Investment integration test #1. Check to ensure that the investment returns match up with the estimated savings calculated previously. | ü
13 | Investment integration test #2. Check that the investment break even time specified matches up with what the data suggests. | ü
14 | Investment integration test #3. Check that the value specified in net profit matches up with what should be expected from the total, minus the system cost. | ü
15 | Investment integration test #4. Check to ensure that the bank investment starts at the same initial value as the panel investment. | ü
16 | Investment integration test #5. Check to ensure that the total end bank investment value specified matches up with what the data is showing. | ü
17 | Earnings integration test #1. Check to ensure that modifying the excess feed-in value also affects the expected return appropriately. | ü
18 | Earnings integration test #2. Check to ensure that the estimated savings directly correspond with the expected power generation values. | ü
19 | Graph integration test. Check to ensure that the values shown on each of the graphs match up with their table equivalents. | ü
20 | Existing user summary. Check the existing user summary to ensure that at the time specified, the values match with what is expected (by viewing tabulated information further down the page). | ü
System Tests
Test # | Test Description | Passes
1 | Check to ensure that an outside user is able to navigate the web application to the calculator. | ü
2 | Check to ensure that an outside user is able to understand all of the terminology in the calculator (assuming they look at the terminology/information page). | ü
3 | Check to ensure that an outside user is able to understand how to input all inormation and retrieve their results. | ü
4 | Check to ensure that an ourside user is able to view the results page and understand what each section means. | ü
5 | Check to ensure that an outside user is able to understand and interpret the graphical outputs and undestand what each section means. | ü
6 | Check to ensure that the site loads and retrieves information in a reasonable amount of time (< 2 seconds). | ü
7 | Check to ensure that incorrect information will inform users of their mistakes and how they can be fixed. | ü
8 | Check to ensure that the application runs sucessfully on the main browsers (IE, Firefox, Chrome, Opera etc). | ü
Non-Functional Acceptance Tests
Test # | Test Description | Passes
1 | Electricity Generation (St. 1): Output is measured on a yearly basis for the lifetime of the product. | ü
2 | Electricity Generation (St. 1): Output is measured in megawatts. | ü
3 | Electricity Generation (St. 1): Each year should be displayed seperately. | ü
4 | Potential Purchaser (St. 2): Multiple common panel options are available for the user to choose between. | ü
5 | Potential Purchaser (St. 2): Each panel has its own power generation, degredation and lifespan with which results are calculated. | ü
6 | Panel Cost Savings (St. 3): Cost savings are in dollar format, with values specified as yearly amounts. | ü
7 | Panel Carbon Savings (St. 4): Carbon savings are displayed in metric tonnes, on a yearly basis. | ü
8 | Break-Even (St. 5): Break even cost is displayed as number of years since the product purchase. | ü
9 | Total Lifetime Savings (St.6): An estimated range of savings is provided, to account for potential variation. | ü
10 | Lifetime Panel Degredation (St. 7): Actual power generation is displayed in medgawatts. With consecutive years displayed side by side. | ü
11 | Total Panel Generation (St. 8): Power genration must exceed specifications for a minimum of ten years. | ü
12 | Potential Earnings (St. 9): Excess power is estimated based on estimated usage and expected generation. | ü
13 | Climate Impact (St. 12): Users are able to select the area they wish to calculate results for. | ü
14 | Comparisons with Other Investments (St. 19): Comparison results are clearly displayed side-by-side for easy comparison. | ü
15 | Error Descriptors (St. 42): All errors should display at least one message. | ü
16 | Error Descriptors (St. 42): All errors should indicate how they can be avoided, not just why they occurred. | ü